## Sheet1
NO. | Category | Work Product | Unit | 22/05/2012 |  |  |  | 24/05/2012 |  |  |  | 29/05/2012 |  |  |  | 31/05/2012 |  |  |  | 2012-03-06 |  |  |  | 2012-05-06 |  |  |  | 2012-07-06
|  |  |  | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D | A | B | C | D
1 | report1
2 | report2 | Software Project Management Plan
3 |  | Problem definition | Page | 24/05/2012 A: 0; 24/05/2012 B: 3; 24/05/2012 C: 0; 24/05/2012 D: 3
4 |  | Project Organization | Page | 24/05/2012 A: 0; 24/05/2012 B: 4; 24/05/2012 C: 0; 24/05/2012 D: 4
5 |  | Microsoft Project Plan | Page
6 |  | Coding Covention | Page | 24/05/2012 A: 0; 24/05/2012 B: 27; 24/05/2012 C: 27; 24/05/2012 D: 27
7 | SRS | SRS document | Page | 24/05/2012 B: 100; 24/05/2012 C: 0; 24/05/2012 D: 400; 29/05/2012 B: 150; 29/05/2012 C: 0; 29/05/2012 D: 400; 31/05/2012 B: 80; 31/05/2012 C: 0; 31/05/2012 D: 400; 2012-03-06 B: 70; 2012-03-06 C: 0; 2012-03-06 D: 400
8 |  | HTML layout | Screen | 2012-03-06 D: 23
9 | MODULE | USE CASE | Screen
10
11 | ADMIN |  |  | 2012-03-06 D: 2
12 |  | CREATE PROJECT | Screen | bar: 2012-03-06 D
13 |  | ADD USER TO PROJECT | Screen | bar: 2012-03-06 D
14 |  | CREATE USER | Screen | bar: 2012-03-06 D
15 |  | CONFIG MODULE | Screen | 2012-03-06 D: 2
16 |  | MANAGE USER | Screen | 2012-03-06 D: 2
17 | TIMESHEET
18 |  | SEARCH | Screen
19 |  | ADD, UPDATE TS | Screen
20 |  | APPROVE, REJECT TS | Screen
|  | REPORT | Screen
|  | EXPORT | Screen
PROJECT
|  | manage info | Screen | bar: 2012-03-06 D
|  | view info | Screen | bar: 2012-03-06 D
|  | report | Screen | bar: 2012-03-06 D
|  | add user to prj | Screen | bar: 2012-03-06 D
|  | manage user | Screen | bar: 2012-03-06 D
|  | cost(budget, expense) | Screen | 2012-03-06 D: 5
|  | risk, issue, change request | Screen | 2012-03-06 D: 4
DMS
|  | search | Screen
|  | create defect | Screen
|  | update defect | Screen
|  | close defect | Screen
|  | report | Screen
|  | export to excel | Screen
DASHBOARD
|  | search | Screen
|  | export to excel | Screen
Screen
| PLANNER |  | Screen
|  | Add task | Screen
|  | update task | Screen
|  | delete task | Screen
|  | * import mpp file | Screen
|  | report | Screen
Screen
| REPORT |  | Screen
|  | report timesheet | Screen
|  | report dms | Screen
|  | report planner | Screen
|  | report project info | Screen
Screen
| REQUIREMENT |  | Screen
|  | add,update, delete requirement | Screen
|  | add use case for requirement | Screen
|  | view requirement info(tracking requirement status) | Screen
|  | export | Screen